{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["sheet1"],"not_rendered":{"external_links":1,"defined_names":2},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"sheet1","index":0,"n_rows":188,"n_cols":11,"rows_kept":188,"merged":[[1,0,1,10],[2,0,2,10],[3,0,3,3],[3,6,3,10],[4,0,5,0],[4,1,5,1],[4,2,5,2],[4,3,5,3],[4,4,5,4],[4,5,5,5],[4,6,4,7],[4,8,5,8],[4,9,5,9],[4,10,5,10],[6,0,6,3],[7,0,7,3],[44,0,44,3],[81,0,81,3],[111,0,111,3],[139,0,139,3],[157,0,157,3],[169,0,169,3],[181,0,181,3],[187,0,187,10]],"flags":["formulas_cached_only"]}
["附表"]
["太仓市2021年重点项目计划表"]
[]
["编制单位：太仓市发展和改革委员会",{"$nulls":5},"单位：万元"]
["序号","项目名称\n","建设性质","建设规模\n","建设起止年限\n","计划总投资\n（万元）","2021年投资计划目标",null,"项目类型","是否2021年新开工","服务推进责任单位"]
[{"$nulls":6},"计划投资\n（万元）    ","建设进度考核目标"]
["合计（172个）",{"$nulls":4},20907350,5885500]
["一、港区（36个）",{"$nulls":4},4416000,1271000]
["☆1","太仓长三角人工智能超算中心","新增新建","规划建设算力达100PFLOPS的超算中心，瞄准智能制造、智慧电厂、智慧港区及5G应用等方向，为周边制造业进行产业赋能与智慧化升级。","2021-2023",600000,200000,"土建竣工。","服务业","是","港区"]
["△2","宝洁供应链创新中心","新增新建","项目拟建设多品类、全链路、数字化、智能化的供应链创新基地。以打造端到端协同供应链为目标，采用新一代SAPHANA大数据计算新技术，以数字孪生（Digital Twins）方式实时优化供应链运作，做到全程可预测、可追踪、可分析、可干预，实现从客户到工厂再到供应商的全程智能透明。在供应链创新中心的推动下，宝洁太仓公司预计在未来十年内实现总产值超800亿元，纳税超150亿元。","2021-2024",300000,50000,"一期试生产。","服务业","是","港区"]
["☆3","太仓海通汽车江海联运物流基地","新增新建","建设4个汽车滚装泊位，形成92万辆整车装卸、物流运输业务，建成江海联运汽车内贸物流枢纽、长三角汽车进出口集散中心。","2021-2023",300000,50000,"完成码头桩基工程10%。","服务业","是","港区"]
["△4","融创高端医疗器械项目","新增新建","项目总占地面积约175亩，总建筑面积约8万平方米，主要产品为年设计生产：化学发光、荧光定量PCR、新冠核酸检测等体外诊断试剂200万盒及配套检测设备；1.5T、3.0T核磁共振机500台套；大热容CT球管1000只；再生医学材料150平方厘米规格生物补片100万张；活性骨粉0.5克规格100万瓶；心脏导管及支架500万套；微波消融针10万支。项目达产后将实现年产值50亿元，纳税5亿元。","2021-2023",200000,50000,"部分主体封顶。","制造业","是","港区"]
["△5","大飞机零部件生产项目","新增新建","一期项目总建筑面积约6.5万平方米，将建设飞机零部件生产基地，主要生产大梁、桁条、翼梁、翼肋、框类等飞机相关零部件，项目达产后将实现年产值50亿元，纳税5亿元。中航工业、法国空客、美国GE将共同参加项目的投资建设。","2021-2022",300000,50000,"部分主体封顶。","制造业","是","港区"]
["△6","玖龙智能装备产业园二期","新增新建","项目总建筑面积65万平方米，其中一期建筑面积4.8万平方米，二期建筑面积12万平方米。项目对标国际一流产业园，建设高品质载体，为汽车零部件、高端装备、功能材料、健康医药、智能制造等企业提供载体服务和厂房租赁。年产1000万米汽车密封条和37万件汽车轮毂。","2021-2022",100000,50000,"完成总工程量30%。","制造业","是","港区"]
["△7","港区医院异地新建","新增新建","项目总建筑面积4.8万平方米，其中地上4万平方米，地下8000平方米。港区医院设计定位为二级甲等综合性医院，床位350张，将成为未来太仓港城片区的中心医院。","2021-2023",49000,20000,"主体基本完成。","民生工程","是","港区"]
["△8","娄城新材料","新增新建","项目建筑面积2.4万平方米，建设新型建筑材料生产基地、研发中心等，项目建成达产后将实现年销售收入16亿元，年税收3000万元。",2021,50000,45000,"竣工投产。","制造业","是","港区"]
["△9","新加坡INGCO电动工具","新增新建","项目将由新加坡INTEVISION有限公司投资建设，总投资7164万美元，注册资本金2388万美元，用地41.6亩，项目包括INGCO品牌总部、锂电直流平台电动工具生产基地、智能家居研发中心等组成部分，预计达产后年销售额1亿美元，研发制造产值3亿元，年税收2000万元。","2021-2022",50000,20000,"主体竣工。","制造业","是","港区"]
["△10","德国宝得高端流量设备","新增新建","项目总建筑面积3.7万平方米，主要从事用于生物医药和环境保护的高端流量设备研发、生产和销售，打造中国区总部，预计全部建成达产后年产阀门35万件，销售收入6亿元，年税收3000万元。","2021-2022",50000,30000,"主体结构封顶。","制造业","是","港区"]
["△11","太仓生物港三期","新增新建","项目建设4.6万平方米GMP厂房，主要引进医疗器械、精准医疗、生物制药等项目。预计达产后实现年产值10亿元，年税收1亿元。 ","2021-2022",100000,60000,"工程基本完工。","科创载体","是","港区"]
[12,"奎克好富顿工业润滑油","新增新建","项目计划总投资1.5亿美元，注册资本5000万美元，用地面积约75亩，项目一期投产后预计年产5万吨各类润滑油脂，年产值7亿元，年税收7000万元。","2021-2023",105000,20000,"部分主体封顶。","制造业","是","港区"]
[13,"凯利昂光电科技新型显示玻璃","新增新建","项目占地面积48.5亩，建设新型显示玻璃液晶面板深加工及薄化设备研发中心，达产后年产值4.5亿元，年税收3000万元。","2021-2022",50000,20000,"主体结构封顶。","制造业","是","港区"]
[14,"中新棠再生医学材料","新增新建","项目总投资1.5亿元，租赁生物港约7100平方米厂房，主要从事生物医药领域再生医学材料的研发、生产和销售。项目建成达产后预计年销售收入3亿元以上，年税收3000万元以上。","2021-2022",15000,15000,"竣工验收。","制造业","是","港区"]
[15,"美国艺康免洗凝胶","新增新建","项目利用现有厂房增加免洗凝胶产线，预计年产出3000吨免洗类消毒产品，满足本地以及亚太地区的市场需求，提供完整的消毒产品和健康保障。",2021,10000,10000,"竣工投产。","制造业","是","港区"]
[16,"德国达必温汽车材料","新增新建","项目租用欧美工业园2号厂房，专业生产玻璃纤维隔热、保温、吸音材料。项目投资2000万美元，注册资本1250万美元，建成达产后，预计年销售收入达2亿元，年税收2000万元。",2021,50000,50000,"竣工投产。","制造业","是","港区"]
[17,"德国森岚吸附式制冷设备","新增新建","项目计划投资建设吸附式制冷设备生产研发基地，将原天津森岚公司搬迁至开发区同高院厂房。项目建成投产后预计年销售额约3600万元，年税收约500万元。",2021,10000,10000,"竣工投产。","制造业","是","港区"]
[18,"瀚德汽车密封系统项目三期","新增新建","瀚德汽车密封系统项目将成立新的外资子公司，新增租赁同高院1号及2号厂房。项目建成达产后，年销售收入达10亿元，年税收5000万元。","2021-2022",50000,20000,"完成设备安装。","制造业","是","港区"]
[19,"思柯拉特二期","新增新建","项目总投资1.2亿元，租赁生物港约2400平方米厂房，主要从事影像医疗器械中核心部件的研发、生产和销售，主要产品为高性能CT球管。项目建成达产后预计年销售收入1亿元以上，年税收1000万元以上。","2021-2022",12000,12000,"竣工投产。","制造业","是","港区"]
[20,"为度生物微球","新增新建","项目总投资1.5亿元，租赁生物港约5260平方米厂房，主要开发、生产、销售各类试剂、药用微球，预计达产后年销售超过2亿元，年税收2000万元。","2021-2022",15000,15000,"竣工投产。","制造业","是","港区"]
[21,"利维鑫血管介入医疗器械","新增新建","项目总投资1亿元，租赁生物港2138.88平方米厂房，主要从事生物医药领域医用介入器械的输送系统及制品的研发、生产和销售，预计全部达产后实现年销售收入5000万元。","2021-2022",10000,10000,"竣工投产。","制造业","是","港区"]
[22,"卓阮生物二期","新增新建","项目主要从事生物医药领域再生医学材料的研发、生产和销售，包括疝修补补片和复合生物补片、硬脑（脊）膜和软组织修补片等高端医疗器械，租赁厂房1.28万平方米，全部达产后实现年销售2亿元以上。",2021,50000,50000,"竣工投产。","制造业","是","港区"]
[23,"中集集装箱二期","新增新建","项目主要从事集装箱生产，新建生产车间5万平方米，新增年产能14.5万个集装箱，新增年产值24亿元。",2021,50000,50000,"竣工投产。","制造业","是","港区"]
[24,"信力通塑料制品生产项目","新增新建","项目总建筑面积1.4万平方米，主要产品为塑料制品，生产工艺为塑料粒子经过加温注塑成型，年产150万件，预计产值5000万元，预计纳税200万元。",2021,10000,10000,"完成设备投入并试生产。","制造业","是","港区"]
["☆25","苏州港太仓港区四期工程","结转续建","项目建设4个5万吨级集装箱泊位及相关配套设施，码头水工结构按靠泊10万吨级集装箱船设计，泊位总长1292米，设计年通过能力200万标箱。","2018-2021",403000,100000,"竣工。","基础设施","否","港区"]
["△26","太仓苏宁环沪电商运营中心","结转续建","项目建筑面积16.4万平方米，将建设苏宁区域电商运营中心，打造集电子商务订单生产中心、结算中心、分拣中心、配送中心、供应链管理及开放平台等功能为一体的综合型园区，成为电商产业园的优秀典范。","2020-2022",350000,50000,"结构封顶。","服务业","否","港区"]
["△27","利洁时全球研发制造中心","结转续建","项目总建筑面积7.2万平方米，建设利洁时全球研发中心、中国最大的生产基地、华东最大的品牌运营和销售总部，新建年产11亿片杜蕾斯安全套及18万吨滴露系列产品。项目投产后预计年产值30亿元，税收1.5亿元。","2019-2021",320000,50000,"竣工投产。","制造业","否","港区"]
["△28","美国斯凯奇中国物流销售中心","结转续建","项目总建筑面积32万平方米，建设世界领先的自动化立体仓库。太仓项目定位为斯凯奇官网电商总部、亚洲物流总仓、分销中心、研发中心、培训中心，并建设品牌特卖店。","2018-2022",240000,20000,"开工建设。","服务业","否","港区"]
["△29","CJ荣庆物流中国总部","结转续建","项目总建筑面积17.8万平方米，建设华东区分拨中心、高度自动化智能仓库、高端冷库及总部大楼。","2018-2022",100000,24000,"竣工投产。","服务业","否","港区"]
[30,"鸣志太仓智能产业基地","结转续建","项目总建筑面积11.8万平方米，建设鸣志生产基地，年产6000万件微型电机，控制电器驱动系统250万台，LED控制与驱动类产品500万台及7000万根线束等产品。项目达产后预计年产值达14亿元，税收1.2亿元。","2019-2021",100000,10000,"竣工投产。","制造业","否","港区"]
[31,"平伊大健康冷链综合产业园","结转续建","项目总建筑面积7.5万平方米，建设集食品药品冷链、医药电商智能配送、OTC西药研究中心、配套金融服务中心于一体的综合智能化产业园。","2019-2021",67000,27000,"竣工验收。","服务业","否","港区"]
[32,"之宝中国加工中心","结转续建","项目总建筑面积约2.4万平方米，年产450万只打火机生产线，同时开发试生产水壶、眼镜、烟斗等相关产品。预计达产后实现年产值8亿元，税收8000万元。","2019-2021",25000,5000,"竣工投产。","制造业","否","港区"]
[33,"太仓科方生物体外诊断试剂及成套检测设备(一期)","结转续建","项目年产化学发光、即时检验等高敏体外诊断试剂盒5000万只，高分子检测、快速诊断检测设备500万套。","2020-2022",150000,10000,"竣工验收。","制造业","否","港区"]
[34,"富兰克油品","结转续建","项目利用存量土地资源,年产2万吨切削液、1万吨切削油、1万吨设备油以及清洗剂、脱模剂、纺丝油剂、淬火液（油）、车用润滑油等。项目预计达产后年产值12亿元，税收6380万元。","2020-2021",50000,20000,"竣工投产。","制造业","否","港区"]
[35,"皇冠假日酒店","结转续建","项目拟建设商业用房4.8万平方米，内含五星级标准酒店一座（2.8万平方米、房间数量不少于220个）及单体规模不小于0.5万平方米的主力旗舰店。","2020-2023",60000,28000,"完成各单体二次结构及砌体结构施工；精装完成30％；机电安装完成50％。","服务业","否","港区"]
[36,"海格物流二期","结转续建","项目总建筑面积3.17万平方米，建设高标准物流仓储设施。","2019-2021",15000,10000,"竣工投产。","服务业","否","港区"]
["二、高新区（36个）",{"$nulls":4},5971500,1669500]
["△1","耐克全自动智能物流中心项目","新增新建","项目为中国物流中心总部，总建筑面积7.39万平方米，引进世界领先全自动物流存取设备，建设国内首创、亚洲第一、全球领先的高等级全自动库架一体仓储设施，成为单体设备能力全国唯一、设备规模亚洲第一的智能物流中心。","2021-2022",150000,100000,"建筑结构封顶。","服务业","是","高新区"]
["☆2","太仓博泽汽车微电机","新增新建","年产微电机等汽车核心系统部件1330万件。","2021-2021",150000,150000,"三期竣工投产。","制造业","是","高新区"]
["△3","炬龙新能源项目","新增新建","项目总占地160亩，其中一期占地60亩，从事各类新能源材料的研发，碳基纳米电池和固态锂电池的生产。项目一期预计实现固态锂电池年产能0.1GWh，碳基电池年产能1GWh。项目二期拟购买土地100亩，建设炬龙新能源总部基地。","2021-2023",165000,50000,"一期竣工投产。","制造业","是","高新区"]
["☆4","太仓康乃德生物医药","新增新建","年产大分子产品CBP-201 300万支，小分子CBP-307 2亿粒。","2021-2022",200000,50000,"厂房建设。","制造业","是","高新区"]
["△5","罗腾堡德风文旅城项目","新增新建","项目位于新浏河南岸，总占地126亩，总建筑面积约9万平方米。建设内容包括德式街区、精品酒店、德国特色餐厅酒吧、德国产品展示交易中心、景观设施和相关配套设施，拟打造高质量对外开放新平台，建设中德经贸、文化、教育交流合作载体，促进太仓中德创新合作。","2021-2022",150000,50000,"主体建设。","服务业","是","高新区"]
["△6","太仓智汇谷项目","新增新建","项目总占地面积168.7亩，总建筑面积33.3万平方米，承接西工大溢出，主要包括创新中心、独栋办公、商务楼宇、研发楼、配套商业等。项目将以“智能+”为核心，结合本地产业基础与高校优势资源，发展汽车、航空相关核心智能硬件与终端、数据应用服务及数字艺术创意内容的闭环产业内容，打造集研发、办公、展示、交流、配套消费与居住为一体的国际化科创社区。","2021-2023",312000,56000,"设计完成，项目桩基工程完成，推进地下结构建设。","科创载体","是","高新区"]
["△7","三友医疗器械项目","新增新建","项目拟购买土地35亩，设立研发中心及生产基地，总投资10亿元，生产骨科内植入医疗器械。达产后可实现年产值5亿元，税收3000万元。","2021-2022",100000,20000,"厂房建设。","制造业","是","高新区"]
["△8","德国飞势新能源汽车部件","新增新建","项目占地22.5亩，建设面积9151平方米，主要生产汽车排气管等产品。达产后，年产汽车排气管40万件，可实现年产值3亿元、税收1500万元。","2021-2022",50000,20000,"厂房建设。","制造业","是","高新区"]
["△9","普来森新能源汽车零部件项目","新增新建","占地32亩，总建筑面积3.742万平方米，主要生产新能源汽车零部件。达产后预计年产值5亿元，税收2000万元。","2021-2022",60000,20000,"主体施工。","制造业","是","高新区"]
["△10","欧托凯勃新能源汽车线束项目","新增新建","占地32.7亩，建设1.6万平方米厂房，主要生产新能源汽车线束产品。达产后年产4460万件汽车线束产品，可实现年产值9亿元，税收4500万元。","2021-2022",60000,20000,"厂房建设。","制造业","是","高新区"]
["△11","陛通半导体设备","新增新建","租赁厂房4400平方米，主要生产高端半导体设备。达产后可实现年产值不低于7亿元，税收3000万元。","2021-2022",50000,20000,"工程基本完工。","制造业","是","高新区"]
["△12","宝沃帕克液压动力项目","新增新建","租赁厂房7191平方米，主要生产液压动力工具70万套。预计达产后销售4亿元，税收3000万元。","2021-2022",50000,20000,"工程基本完工。","制造业","是","高新区"]
["△13","通快激光发生器项目","新增新建","通快集团将太仓升级为亚太区总部，拟将激光发生器、高频发生器等核心产品本地化生产，并提升、整合研发中心、培训中心、结算中心等功能。项目增资人民币1亿元。项目达产后预计新增年产值5亿元。",2021,50000,50000,"竣工投产。","制造业","是","高新区"]
[14,"光昛智能项目","新增新建","占地20亩，生产电致变色智能节能薄膜特殊的半导体纳米薄膜材料。达产后年产不低于6万片智能玻璃，可实现产值3亿元，纳税2000万元。","2020-2021",50000,20000,"厂房结构封顶。","制造业","是","高新区"]
[15,"中科院金属所新一代航空发动机低压涡轮叶片—钛铝合金近净成型项目","新增新建","项目租赁航空新材料创新园1万平方米厂房。项目主要生产航空发动机叶片、航空航天钛合金铸件、军工国防钛合金铸件、民用钛合金铸件等。项目达产后可实现年产值5亿元。","2021-2022",50000,50000,"竣工投产。","制造业","是","高新区"]
[16,"大学城商业街项目\n（暂定名）","新增新建","项目总占地面积88.96亩，总建筑面积11.825万平方米，主要包括沿街商业、商业盒子、精品酒店、商务办公等。项目将以“潮玩”为主题，打造业态多元化、高品质生活，传递多元化生活体验，全面焕新升级城市商业。","2021-2023",70000,12000,"设计完成，项目开工，完成桩基工程，力争完成地下结构建设。","服务业","是","高新区"]
[17,"合兴汽车电子扩建项目","新增新建","总建筑面积8100平方米，主要生产汽车传感器等零部件。","2020-2021",21000,20000,"竣工投产。","制造业","是","高新区"]
[18,"施迈茨真空设备项目","新增新建","占地40亩，建筑面积1.73万平方米，主要生产真空设备,年产真空设备及部件18000件、搬运设备及部件20000件。达产后可实现产值2亿元。","2020-2021",20000,20000,"设备安装调试。","制造业","是","高新区"]
[19,"卓能航空汽车电子项目","新增新建","扩建1.2万平方米，主要生产新能源汽车逆变器，预计年产新能源汽车逆变器4万个、航空汽车电子PCBA1万片。达产后可实现年产值10亿元，税收6200万元。","2021-2022",10000,5000,"厂房竣工验收。","制造业","是","高新区"]
[20,"福驶特汽车零部件项目","新增新建","租赁厂房4300平方米，主要生产汽车涡轮增压部件60万套。项目达产后可实现年产值1.18亿元，年纳税额500万元。","2020-2021",10000,10000,"竣工投产。","制造业","是","高新区"]
[21,"智行畅联项目","新增新建","租赁厂房4000平方米，主要生产智能车载设备等。达产后可实现年产值3亿元，实现税收2000万元。","2020-2021",10000,10000,"竣工投产。","制造业","是","高新区"]
[22,"裕克施乐四期","新增新建","占地15亩，分两期开发：四期和五期。首先开发四期，建设三部分：全自动物流中转仓，作为整个工厂的产品中转仓，提升产品中转效率；5层研发大楼共6817平方米；6层建筑型停车场，每层33个车位。达产后年销售额增加2亿元，年纳税额增加750万元。","2020-2021",10000,10000,"竣工投产。","制造业","是","高新区"]
[23,"菲码智能科技","新增新建","项目占地20亩，总建筑面积1.7万平方米，项目主要生产标识系统，年产标识打印机50万台、标识模切耗材6.5亿片。达产后可实现年产值2亿元，税收1000万元。","2020-2021",10000,10000,"竣工投产。","制造业","是","高新区"]
[24,"瑞基执行器项目","新增新建","租赁厂房4000平方米，主要生产航空用执行器。达产后年产执行器2万台，产值不低于2亿元，税收1500万元。","2020-2021",10000,10000,"竣工投产。","制造业","是","高新区"]
["△25","舍弗勒太仓新基地项目","结转续建","项目占地136.54亩，总建筑面积约8.18万平方米。项目分二期开发建设，一期于2020年6月开工，预计2022年初竣工。主要生产新能源汽车零部件、航空轴承、特种设备等产品，达产后可新增年产值30亿元。","2020-2022",200000,30000,"一期结构封顶。","制造业","否","高新区"]
["△26","苏州清华天镜湖智能装备科创园项目","结转续建","项目占地253亩，总投资30亿元，总建筑面积35.58万平方米，是由清华力合重资产投入建设并持有运营的科技创新载体，将聚焦“智能网联汽车”和“3D打印材料”两大产业，形成具有国际影响力的细分领域科技创新中心。","2020-2024",300000,100000,"一期竣工；二期主体结构完成90%；三期主体结构封顶。","科创载体","否","高新区"]
["△27","太仓高教园区","结转续建","西北工业大学太仓校区总占地面积1576亩，总建筑面积94.3万平方米，总投资约50亿元；\n西交利物浦大学太仓校区占地约546亩，总建筑面积49.7万平方米，总投资约43亿元，已于2019年4月开工，2021年9月部分启用；\n市政道路设施约5公里；\n西工大长三角研究院3.78万平方米。","2018-2025",948000,200000,"一、西工大太仓校区：一期项目竣工投入使用；\n二、西浦太仓校区：宿舍区项目竣工，具备使用条件；教学区：项目结构封顶，开始装饰施工；\n三、科教创新区一期基础设施：学院路、规划一路、规划二路、十八港路完成竣工验收，万金路、富达路项目实施，洙泾路项目启动。","民生工程","否","高新区"]
["△28","联合利华食品基地项目","结转续建","项目总建筑面积3.3万平方米，项目建设中国区食品类综合生产基地，年产冷冻饮品7.6万吨。项目建成后年产值20亿元，可实现税收5000万元。","2020-2021",150000,120000,"竣工投产。","制造业","否","高新区"]
["△29","沪工新建机器人柔性生产线项目","结转续建","项目建设20万平方米生产车间及研发用房，主要生产激光焊接与切割成套装备、焊接机器人柔性生产线、数字化焊接电源等智能化装备,年产数字化电焊机30万台，先进激光切割机1000台，机器人柔性生产线150条。竣工达产后预计年产值50亿元。","2018-2022",320000,20000,"二期结构封顶。","制造业","否","高新区"]
[30,"康斐尔空气净化设备项目","结转续建","项目占地60亩，总建筑面积3万平方米,主要生产空气净化设备。达产后年产过滤设备2400台，可实现年产值10亿元，税收1亿元。","2020-2021",60000,50000,"竣工投产。","制造业","否","高新区"]
[31,"西交利物浦（太仓）附属学校","结转续建","新建教育用房总建筑面积11万平方米。","2020-2021",60000,25000,"竣工。","民生工程","否","高新区"]
[32,"复游文旅城","结转续建","太仓复游城是复星旅游文化集团打造的旅游目的地项目。总开发区域为1500亩，总建设规模约180万平方米。项目拥有阿尔卑斯雪世界、狼队运动公园、欧风街等三项核心旅游资源，Club  Med Joyview度假村、Cook’s Club&Cook’s Home系列酒店以及配套高端国际社区，是FOLIDAY复星旅文生态圈下的综合型国际休闲度假目的地。","2018-2023",2000000,250000,"欧风街及CLUB MED酒店、阿尔卑斯雪世界全面开工；狼队运动公园、Cook’s Club&Cook’s Home系列酒店完成报批报建；住宅正常推进，幼儿园完成交付。","服务业","否","高新区"]
[33,"共进科技大厦","结转续建","项目总建筑面积约5万平方米，其中：地上建筑面积3.3万平方米，地下室面积1.7万平方米；配套绿化面积4293.48平方米，容积率为2.3；绿地率为30.00%；建筑密度为20.03%。","2018-2021",36000,15000,"外幕墙工程完成，开始室外配套施工。","科创载体","否","高新区"]
[34,"麦格纳汽配项目二期","结转续建","项目占地28.3亩，总建筑面积2.2万平方米，项目生产车用光学器件和电子控制系统，年产车灯、执行器、装饰灯等总计4.4亿个，达产后可实现年产值8亿元，税收5000万元。","2020-2021",32500,24500,"竣工投产。","制造业","否","高新区"]
[35,"质卓科创产业园","结转续建","占地30亩，投资总额2.5亿元，项目总建筑面积4万平方米，建设智能装备制造产业园。","2020-2021",25000,15000,"竣工投产。","制造业","否","高新区"]
[36,"美源供应链项目","结转续建","项目总建筑面积3万平方米，建设智能冷链配送中心，主要从事冰淇淋、巧克力及冷冻包装食品的储存，储存量380万箱。建成后年营业收入3.1亿元，年纳税额1900万元。","2020-2021",22000,17000,"竣工投产。","服务业","否","高新区"]
["三、城厢镇（29个）",{"$nulls":4},1829000,731000]
["△1","事达同泰汽车轻量化系统项目","新增新建","总建筑面积18万平方米，致力于汽车轻量化及系统零部件的生产研发并提供汽车轻量化系统集成解决方案，达产后年产汽车轻量化排气系统4500万件（套）、高精密汽车发动机管路1500万件（套）、轻量化底盘系统及零部件100万件（套）、新能源汽车智能驾驶制动关键部件50万件（套），预计年产值25亿元，税收1.6亿元。","2021-2023",200000,50000,"主体厂房建设完成20%。","制造业","是","城厢镇"]
["△2","中科赛诺绿色安全型钠盐储能电池及系统项目","新增新建","总建筑面积约4万平方米，主要研发生产水系钠盐储能电池及系统，年产水系钠盐储能电池及系统2GWh，满足包括电力调峰、可再生能源并网、备用电源等固定式储能场景和铅酸电池替代等国内外储能市场需求。达产后，预计实现产值20亿元，税收1亿元。","2021-2023",150000,50000,"主体厂房建设完成40%。","制造业","是","城厢镇"]
["△3","中科院上硅所高性能陶瓷基复合材料项目","新增新建","总建筑面积4万平方米，主要从事高性能碳化硅陶瓷基复合材料、连续氧化铝基陶瓷纤维等高性能陶瓷材料研发生产，产品被广泛运用在国防、航空航天、汽车、电力输送等军民两用领域。达产后，年产高性能碳化硅陶瓷基复合材料、连续氧化铝基陶瓷纤维等陶瓷材料50吨，高性能陶瓷刹车系统100万件以及耐磨损构件50万件。预计实现产值5亿元，税收4000万元。","2021-2022",100000,50000,"主体厂房建设完成40%。","制造业","是","城厢镇"]
["△4","骏伟精密塑胶太仓总部项目","新增新建","总建筑面积约6万平方米，主要研发、生产汽车用精密注塑件。达产后，预计实现产值8亿元，税收5000万元。","2021-2023",200000,50000,"主体厂房建设完成30%。","制造业","是","城厢镇"]
["△5","中欧智能装备项目","新增新建","总建筑面积约4万平方米，主要研发、生产工业自动控制系统装置、智能关键基础零部件。达产后，预计实现产值10亿元，税收6000万元。","2021-2022",100000,30000,"主体厂房建设完成50%。","制造业","是","城厢镇"]
["△6","海美工业自动控制系统装置及智能车载设备项目","新增新建","总建筑面积8.5万平方米，主要以新一代信息技术、智能装备制造、新材料、新能源汽车部件等新兴产业为主导产业，形成以中小规模生产、研发为主的产业孵化加速器。达产后，预计实现产值5亿元，税收3000万元。","2021-2022",100000,30000,"结构封顶。","制造业","是","城厢镇"]
["△7","锐泽先进复合材料项目","新增新建","总建筑面积7万平方米，主要研发、生产风电和汽车用碳纤维材料。达产后，预计实现产值10亿元，税收7000万元。","2021-2022",100000,30000,"结构封顶。","制造业","是","城厢镇"]
["△8","金璞航空航天用新型材料项目","新增新建","租赁5万平方米厂房，主要研发、生产高性能复合材料，应用于风电、汽车、航天领域。投产后，预计实现产值12亿元，税收1亿元。","2021-2022",53000,20000,"装修完成，部分设备进场。","制造业","是","城厢镇"]
["△9","讯极声光智能检测装备项目","新增新建","总建筑面积3万平方米，主要研发、生产声光电检测设备、海关集装箱空箱检查设备、专用机器人。达产后预计实现产值2亿元，税收1500万元。","2021-2022",50000,20000,"主体厂房建设完成60%。","制造业","是","城厢镇"]
[10,"瑞铁智能数控机床项目","新增新建","总建筑面积1.5万平方米，主要研发、生产智能数控激光切割机床、数控工业机床等产品。达产后，预计实现产值5亿元，税收3000万元。","2021-2022",50000,20000,"主体厂房建设完成60%。","制造业","是","城厢镇"]
[11,"承捷高端载运部件项目","新增新建","总建筑面积1.5万平方米，主要研发、生产汽车、航空零部件、高端半导体设备。达产后，预计实现产值3亿元，税收1600万元。","2021-2022",50000,20000,"主体厂房建设完成50%。","制造业","是","城厢镇"]
[12,"海德鲁精密合金型材项目","新增新建","租赁2.5万平方米厂房，主要研发、生产各类汽车铝型材。达产后，预计实现产值4亿元，税收2000万元。",2021,36000,36000,"竣工投产。","制造业","是","城厢镇"]
[13,"嘉昆太核心产业园科创配套项目","新增新建","总建筑面积15万平方米，引入一批科技研发、人才项目，形成产业化项目孵化基地。","2021-2022",100000,20000,"主体建筑建设完成20%。","科创载体","是","城厢镇"]
[14,"中科（苏州）智慧产研城项目","新增新建","租赁厂房5万平方米，主要研发、生产VR交互设备等。达产后，预计实现产值5亿元，税收2000万元。",2021,30000,30000,"竣工投产。","科创载体","是","城厢镇"]
[15,"圣惠先进医疗科技项目","新增新建","总建筑面积1.8万平方米，主要研发、生产医用新材料、医疗器械等产品。达产后，预计实现产值2亿元，税收1100万元。","2021-2022",30000,10000,"主体厂房建设完成50%。","制造业","是","城厢镇"]
[16,"博可层压涂覆系统制造项目","新增新建","租赁1.6万平方米厂房，主要研发、生产层压机、涂层机等设备。达产后，预计实现产值2亿元，税收1300万元。","2021-2022",25000,15000,"进场装修。","制造业","是","城厢镇"]
[17,"泓佑泓博自动化控制项目","新增新建","总建筑面积1万平方米，主要研发、生产工业探伤仪等工业控制装备（系统）。达产后，预计实现产值2亿元，税收1000万元。","2021-2022",25000,10000,"主体厂房建设完成30%。","制造业","是","城厢镇"]
[18,"福仁得智能载运装备项目","新增新建","总建筑面积1.5万平方米，主要研发、生产智能物流设备、物流机器人，并提供智慧仓储系统的集成及整体解决方案。达产后，预计实现产值2亿元，税收1000万元。","2021-2022",20000,10000,"主体厂房建设完成50%。","制造业","是","城厢镇"]
[19,"巨跃汽车智能传动科技项目","新增新建","总建筑面积3万平方米，主要研发、生产智能车载设备、轴承、齿轮和传动部件。达产后，预计实现产值5亿元，实现税收3000万元。","2021-2022",100000,50000,"主体厂房建设完成30%。","制造业","是","城厢镇"]
[20,"博特智慧物流设备项目","新增新建","总建筑面积1万平方米，主要研发、生产仓储物流智能设备。达产后，预计实现产值1亿元，税收1000万元。","2021-2022",20000,10000,"主体厂房建设完成60%。","制造业","是","城厢镇"]
[21,"富利城智能装备项目","新增新建","主要研发、生产工业自动控制系统装置、智能车载设备。达产后，预计实现产值5000万元，税收300万元。",2021,20000,20000,"竣工投产。","制造业","是","城厢镇"]
[22,"manaflex新能源车用动力电池包项目","新增新建","租赁5000平方米厂房，主要专注于车用电池包零件制造，模块整合与新制程/产品开发，是特斯拉重要供应商。年产新能源汽车电池包20000套。达产后预计实现产值3.5亿元，税收3000万元。","2021-2022",80000,50000,"装修完成，部分设备进场。","制造业","是","城厢镇"]
[23,"阿美泰克智能换热装备项目","新增新建","总建筑面积1万平方米，主要研发、生产智能换热装备（系统）。达产后，预计实现产值2亿元，税收1000万元。","2021-2022",30000,20000,"结构封顶。","制造业","是","城厢镇"]
[24,"格林莱特汽车轻量化内饰件项目","新增新建","总建筑面积1.5万平方米，主要研发生产汽车轻量化植绒内饰件等产品。达产后，预计实现产值3亿元，税收1500万元。","2021-2022",30000,15000,"主体厂房建设完成50%。","制造业","是","城厢镇"]
[25,"富照新能源汽车零部件项目","结转续建","项目总建筑面积3.1万平方米，主要研发制造新能源汽车零部件，并提供相关技术服务与技术咨询。达产后，预计实现产值3亿元，税收2000万元。","2020-2021",20000,10000,"竣工投产。","制造业","否","城厢镇"]
[26,"聿联汽车电子项目","结转续建","项目总建筑面积5万平方米，项目主要研发制造车用核心电子接插件和智能制造（物流）设备系统集成。达产后，预计实现产值3亿元，税收2500万元。","2020-2022",30000,15000,"竣工投产。","制造业","否","城厢镇"]
[27,"万宸环保装备项目","结转续建","项目总建筑面积2万平方米，主要研发制造固废环保循环处理设备及系统，并提供运营解决方案。达产后，预计实现产值2亿元，税收1500万元。","2020-2021",15000,10000,"竣工投产。","制造业","否","城厢镇"]
[28,"联禾厚普新能源汽车零部件项目","结转续建","项目总建筑面积2万平方米，扩建新能源汽车零部件项目，年产精密部件50万套。达产后，预计实现产值2亿元，税收1200万元。","2020-2021",15000,10000,"竣工投产。","制造业","否","城厢镇"]
[29,"致美达建筑产业现代化装配式部件项目","结转续建","项目总建筑面积5.4万平方米，新建年产装配式预制构件18万立方米。达产后，预计实现产值5亿元，税收4500万元。","2020-2022",50000,20000,"结构封顶。","制造业","否","城厢镇"]
["四、沙溪镇（27个）",{"$nulls":4},1985000,643000]
["☆1","太仓聪明制药新建缓控释制剂","新增新建","年产SPPO-1、SPPO-2等产品，年产能40亿粒/片；以及SPPO-3、SPPO-4等大分子口服产品，年产能60亿粒/片。","2021-2024",300000,50000,"取得施工许可证，进行主体建设。","制造业","是","沙溪镇"]
["△2","太仓星药港糖尿病药械项目","新增新建","项目占地约122亩，总建筑面积约14万平方米，总体围绕“药物+器械”多元化，依托长效药物平台、干细胞平台、基因技术平台等相关技术，预计年产蛋白600千克、细胞治疗药物1600人份、基因载体300克；预计年产胰岛素泵、植入式生物胰腺等医疗器械5000件。项目预计5年达产，达产后实现年产值10亿元以上。","2021-2024",300000,50000,"主体结构建设。","制造业","是","沙溪镇"]
["△3","西域供应链华东基地项目","新增新建","项目占地约106亩，总建筑面积约21.3万平方米，将建设成以工业互联网MRO行业为特色的供应链中心，引入西域MRO供应链华东结算中心，同时建设具有国际标准的现代化仓储配送中心等。项目将对周边工业产能提升、工业互联网发展、产业资源的有效整合，带来更完善更具有科技助推力的产业链配套，将成为繁荣区域经济发展的示范性新经济服务平台之一。","2021-2025",200000,100000,"主体结构建设。","服务业","是","沙溪镇"]
["△4","ESR智能产业园项目","新增新建","项目用地230亩，计划招引制造业、生产性服务业、生产性物流等产业。预计实现年度税收7000万元。","2021-2024",100000,30000,"主体建设。","科创载体","是","沙溪镇"]
["△5","泰应新建医疗器械产业化项目","新增新建","项目占地面积20亩，新建纤维环缝合器等医疗器械产品生产项目。项目总建筑面积3.37万平方米，量产后实现年销售额1亿元，实现年税收1000万元。","2020-2022",50000,30000,"完成主体建设。","制造业","是","沙溪镇"]
["△6","三乐新建微波康复器械产业化项目","新增新建","项目占地面积25亩，总建筑面积约2.6万平方米，建设微波康复医疗器械产业化基地。正式投产后可年产微波治疗机1万台、产后康复治疗仪8000台、骨创伤治疗仪2000台，达产后预计实现年产值3亿元，税收3000万元。\n","2021-2022",50000,30000,"完成主体建设。","制造业","是","沙溪镇"]
["△7","百因诺新建生物CDMO项目","新增新建","项目一期厂房面积约为1.2万平方米，目标为建成2万升总细胞培养体积的CDMO生产基地，同时建成年产固体培养基1000吨、液体培养基50万升的生产基地，预计实现年产值10亿元。","2021-2022",50000,30000,"完成装修。","制造业","是","沙溪镇"]
[8,"洋邦机械设备项目","新增新建","项目占地面积约15.3亩，建筑面积1.5万平方米，主要生产智能设备及各类专用、通用设备。预计年产值1.5亿元，税收800万元。","2021-2023",20000,10000,"主体建设。","制造业","是","沙溪镇"]
[9,"迈迪赫兹新建医疗器械项目","新增新建","生产、加工、销售模具及零部件、温控器、塑料注塑机、机械零部件、医疗器械等。","2021-2023",50000,30000,"主体建设。","制造业","是","沙溪镇"]
[10,"桑林汽车零部件项目","新增新建","项目总建筑面积约5750平方米，建成后，可年产汽车零部件1000万件，实现年销售额1亿元，实现税收550万元。","2021-2023",15000,10000,"主体建设。","制造业","是","沙溪镇"]
[11,"美仑新建细胞培养基生产项目","新增新建","项目租赁七溪生物硅谷厂房4418平方米，用来建设细胞培养基生产项目。总投资5000万元，项目建成后，可年产细胞培养基100万升，实现年销售额8000万元。","2020-2021",10000,10000,"完成装修。","制造业","是","沙溪镇"]
[12,"兰立生物新建药物研发服务项目","新增新建","项目租赁创业园二期厂房约1000平方米，用来建设药效、药筛测试服务项目。项目建成后，预计年产值1000万元，税收100万元。","2021-2022",10000,10000,"完成装修。","制造业","是","沙溪镇"]
[13,"环琪新建塑料制品项目","新增新建","占地约60亩，总投资3亿元，建筑面积约2万平方米，预计新增塑料制品6800吨，实现年销售额4亿元，税收3000万元。","2021-2022",30000,20000,"主体建设。","制造业","是","沙溪镇"]
[14,"亨盛新建展示道具项目","新增新建","占地25亩，总投资2亿元，建筑物面积约2.3万平方米，从事展示道具的设计与生产，预计年产值2.5亿元，税收1300万元。","2021-2022",25000,15000,"主体建设。","制造业","是","沙溪镇"]
[15,"舒展新建机械设备项目","新增新建","租赁太仓平谦智能制造产业园约4200平方米厂房，总投资1.5亿元，从事环保设备、机电及通用设备的生产销售，预计实现年产值1亿元，税收500万元。",2021,15000,15000,"投产。","制造业","是","沙溪镇"]
[16,"龙阔新建动物疫苗项目","新增新建","租赁七溪生物硅谷1500平方米厂房，总投资1亿元，从事动物疫苗、生物佐剂的研发生产。预计年销售额5000万元，税收400万元。",2021,10000,10000,"完成装修。","制造业","是","沙溪镇"]
[17,"拓维新建药品综合CRO服务项目","新增新建","租赁七溪生物硅谷2000平方米厂房，总投资1亿元，建设药品临床前药理、药效、药代动力学研发外包服务基地。建成后预计年服务额2000万元，税收200万元。",2021,10000,10000,"完成装修。","制造业","是","沙溪镇"]
[18,"康润新建核酸酶制剂项目","新增新建","租赁七溪生物硅谷1500平方米厂房，总投资1亿元，从事核酸平台核心酶产品研发和生产，预计年产值2500万元，税收200万元。",2021,10000,10000,"完成装修。","制造业","是","沙溪镇"]
[19,"特姆威新建乳腺癌光声成像仪项目","新增新建","租赁生物医药产业园1500平方米厂房，总投资1亿元，从事乳腺癌光声检测系统的研发和生产。4年内实现产品上市，产值预计可达13亿元。",2021,10000,10000,"完成装修。","制造业","是","沙溪镇"]
["△20","昭衍生物硅谷新药创制中心项目","结转续建","项目总投资50亿元。一期项目主要建设生物医药公共实验平台、CMO药品生产公共服务平台和GMP标准厂房、生物医药企业培育基地。其中8#地块（新药创制中心项目）占地面积120亩，建筑面积13.88万平方米。","2020-2022",500000,50000,"完成项目工程量50%。","科创载体","否","沙溪镇"]
[21,"太仓祥平智能产业园","结转续建","项目新建高标准厂房约12万平方米，建成后主要引进智能制造、高端装备等产业项目。","2019-2023",95000,20000,"一期1234#竣工投产，二期前期报建。","科创载体","否","沙溪镇"]
[22,"远溪食品","结转续建","项目总建筑面积约5.9万平方米，从事低温食品加工及自用冷链配送项目。","2020-2022",50000,20000,"主体竣工。","制造业","否","沙溪镇"]
[23,"康辉新建医疗器械项目","新增新建","占地8亩，建筑面积5000平方米，年产医疗器械4900台，养老辅具700台，实现年产值1亿元，税收500万元。",2021,10000,10000,"竣工。","制造业","是","沙溪镇"]
[24,"娄创新建新材料项目","新增新建","占地42.24亩，建筑面积约2万平方米，年产新型墙体材料2000万件，实现年产值5亿元，税收2150万元。",2021,30000,30000,"主体竣工。","制造业","是","沙溪镇"]
[25,"超意新建汽车零部件项目","新增新建","占地15亩，建筑面积1万平方米，年产汽车零部件80000套/件，实现年产值1.5亿元，税收800万元。","2021-2022",12000,10000,"主体建设。","制造业","是","沙溪镇"]
[26,"斯伟特新建家用电梯项目","新增新建","租赁厂房4600平方米，总投资1亿元，新建家用电梯生产项目，年产家用电梯2400台，实现产值1.2亿元，税收500万元。",2021,10000,10000,"投产。","制造业","是","沙溪镇"]
[27,"丽固新建日用品项目","新增新建","租赁厂房1.26万平方米，总投资1.3亿元，新建日用品生产项目，年产水解纸1320吨，水解湿巾2600万包，实现产值1.5亿元，税收700万元。",2021,13000,13000,"投产。","制造业","是","沙溪镇"]
["五、浏河镇（17个）",{"$nulls":4},3750250,893000]
["△1","铃兰医疗用品新建医疗用品、卫生用品项目","新增新建","项目总建筑面积5万平方米，建成后预计年生产医疗用棉400吨、医用口罩2.2亿枚、化妆棉4000吨、消毒棉1200万盒。","2021-2022",50000,30000,"开工建设。","制造业","是","浏河镇"]
["△2","海泰汽配新建新能源汽车零部件项目","新增新建","项目总建筑面积2.6万平方米，建成后预计年生产新能源汽车覆盖件500万件、内饰件500万件。","2021-2022",105000,60000,"开工建设。","制造业","是","浏河镇"]
[3,"祥泰旅游新建酒店项目","新增新建","项目总建筑面积15.1万平方米，项目布局以酒店主楼为中心，规划建设国际会议中心、饮食中心、娱乐中心、运动中心、健康中心、商业中心等。","2021-2022",100000,50000,"开工建设。","服务业","是","浏河镇"]
[4,"悦格电子商务新建温控供应链智慧项目","新增新建","项目总建筑面积3万平方米，建成后预计年产品加工周转量约40万吨。","2021-2022",36000,26000,"开工建设。","服务业","是","浏河镇"]
[5,"贝茵佳智能科技新建医疗器械、制冷设备、实验设备产品项目","新增新建","项目总建筑面积2.8万平方米，建成后预计年生产医疗器械3万台、制冷设备3万台、实验设备2万台。","2021-2022",50000,30000,"开工建设。","制造业","是","浏河镇"]
[6,"新泽智能制造新建智能机器人项目","新增新建","项目总建筑面积4万平方米，建成后预计年生产工业智能机器人2500套、自动化设备线1000套。","2021-2022",50000,30000,"开工建设。","制造业","是","浏河镇"]
[7,"优缘新材料新建机场高铁用铝基复合新材料项目","新增新建","项目总建筑面积3.3万平方米，建成后预计年生产机场用铝基复合新材料4吨、高铁用铝基复合新材料6吨。","2021-2022",50000,30000,"开工建设。","制造业","是","浏河镇"]
[8,"弘熠昇航空、汽车精密机械零部件项目","新增新建","项目总建筑面积1.6万平方米，建成后预计年生产机场用飞机起落架配件3000套、汽车零部件10万套。","2021-2022",50000,30000,"开工建设。","制造业","是","浏河镇"]
[9,"奇安迅先进载运核心零部件项目","新增新建","项目总建筑面积1万平方米，建成后预计年生产空间站组合支架、锁紧机构、转换机构等航空航天用零部件5000套，船舶低速、中速柴油机主机零部件等3万套。","2021-2022",30000,20000,"开工建设。","制造业","是","浏河镇"]
["△10","太仓恒大文旅城","结转续建","项目总建筑面积50万平方米，规划建设全室内、全天候、全季节童话神话公园，配套会展中心、商业街等。","2017-2022",3000000,500000,"乐园单体主体全面竣工。","服务业","否","浏河镇"]
[11,"浩达汽贸华东电商中心项目","结转续建","项目总建筑面积12万平方米，建成后预计年进出仓汽车发动机电脑控制器、发电机及其他零配件总量1000万次。","2020-2021",57000,22000,"竣工。","服务业","否","浏河镇"]
[12,"荷顿智能制造新建智能化机器人焊接生产线、精密型生产控制精度设备","结转续建","项目总建筑面积2.5万平方米，建成后预计年生产智能化机器人焊接生产线1万套、精密型生产控制精度设备1.5万套。","2020-2021",30000,10000,"竣工。","制造业","否","浏河镇"]
[13,"意欣智能科技新建智能家电组建、汽车仪器仪表组建及内饰件","结转续建","项目总建筑面积2.35万平方米，建成后预计年生产智能家电组建500万套、汽车仪器仪表组建及内饰件20万套。","2020-2021",30000,10000,"竣工。","制造业","否","浏河镇"]
[14,"缘福汽配新建汽车零部件项目","新增新建","项目总建筑面积6000平方米，建成后预计年生产汽车零部件4000万件（其中冲压件3000万件、注塑件1000万件）、模具500件。","2021-2022",10000,6000,"开工建设。","制造业","是","浏河镇"]
[15,"巨泰电机新建太阳能光伏支架及发电机配套件项目","新增新建","项目总建筑面积5000平方米，建成后预计年生产太阳能光伏支架300套、发电机配套件30套。","2021-2022",10000,7000,"开工建设。","制造业","是","浏河镇"]
[16,"贯龙电磁线新建风能发电用特种线圈项目","新增新建","项目总建筑面积2万平方米，建成后预计年生产风电用特种线圈5000吨。","2021-2022",50000,20000,"开工建设。","制造业","是","浏河镇"]
[17,"新建小学、初中项目","新增新建","新建8轨48班小学一所、12轨36班初中一所，总占地面积约10.33万平方米，新建建筑面积6.47万平方米，计容建筑面积5.61万平方米；新建两栋行政楼、一栋报告厅、两栋专用教室、两栋普通教室、一栋体育馆（食堂）、三个门卫室（家长等候室）、两个配电房、两个看台等。","2021-2023",42250,12000,"开工建设。","民生工程","是","浏河镇"]
["六、璜泾镇（11个）",{"$nulls":4},739000,240000]
["△1","太仓大数据网络设备","新增新建","项目总占地面积200亩，建筑面积25万平方米，建设智能制造车间和研发中心。研发和生产新一代超高性能云计算网络核心交换系统和存储系统等智能网络设备，该交换系统具有高容量、大缓存、虚拟化、模块冗余化等特征，可满足新一代数据中心算力倍增、超大规模组网的需求。项目达产后预计年产高性能交换机35万台，年销售约40亿元，税收2亿元。","2021-2024",500000,170000,"完成主体结构30%。","制造业","是","璜泾镇"]
[2,"高端调味品项目","新增新建","项目占地21亩，计划总建筑面积2.8万平方米，主要从事复合调味料及酱料的生产。项目达产后年销售收入可达4.5亿元，年税收2000万元。","2020-2022",10000,8000,"完成主体结构80%。","制造业","是","璜泾镇"]
[3,"承筑商业综合体项目","新增新建","项目占地16.8亩，建设星级酒店及开放式商业街区。","2020-2023",30000,10000,"完成主体结构50%。","服务业","是","璜泾镇"]
[4,"同臣环保设备项目","新增新建","项目占地65亩，主要研发与生产污水、污泥处理等环保装备，以及污泥深度脱水、黑臭水体治理、热解气化、热解炭化、低温干化等污泥污水处理系统集成服务。","2021-2022",30000,15000,"完成主体结构80%。","制造业","是","璜泾镇"]
[5,"向敬自动化设备项目","新增新建","项目租赁厂房3000平方米，主要从事硅片加工自动化设备制造，预计年产值1亿元。","2021-2022",5000,3000,"部分投产。","制造业","是","璜泾镇"]
[6,"总部商业楼项目","新增新建","占地13亩，建筑面积2万平方米，将建成集总部、研发、办公、商业于一体的综合性商业写字楼，打造璜泾南部新城的新地标。","2021-2023",10000,5000,"完成主体结构50%。","服务业","是","璜泾镇"]
[7,"栋思尧电力设备项目","新增新建","项目占地29亩，计划总建筑面积3万平方米，主要从事电气设备、医疗设备的研发与生产。项目达产后年销售收入可达3亿元，预计税收1500万元。","2021-2022",15000,4000,"完成主体结构50%。","制造业","是","璜泾镇"]
[8,"5G智慧照明项目","新增新建","项目占地27.8亩，计划建筑面积3.5万平方米。项目达产后年产智慧路灯2万件及5G通信设备2万件。 ","2021-2022",14000,2000,"完成主体结构30%。","制造业","是","璜泾镇"]
[9,"智能制造产业园","结转续建","项目总建筑面积12万平方米，建设智能制造园区。","2019-2023",90000,5000,"完成二期主体结构60%。","科创载体","否","璜泾镇"]
[10,"宜晟汽车流体零部件","结转续建","项目总建筑面积2.85万平方米，建成后可年产汽车零部件5000万个，实现年产值3亿元。","2020-2022",20000,10000,"主体结构全部完成。","制造业","否","璜泾镇"]
[11,"佰顿金属复合材料","结转续建","项目主要从事各类金属复合材料的研发与生产，产品广泛应用于汽车、高铁、建筑等领域。项目达产后，年销售可达6亿元。","2020-2022",15000,8000,"主体结构全部完成。","制造业","否","璜泾镇"]
["七、双凤镇（11个）",{"$nulls":4},590000,270000]
[1,"瑞昭丰新建智能化监测设备项目","新增新建","建造建筑物1.05万平方米，其中生产车间9000平方米，办公及辅助用房1500平方米。项目建成后年产智能探伤仪80-100台，年销售1亿元，利税900万元。","2021-2022",5000,5000,"主体结构封顶。","制造业","是","双凤镇"]
[2,"步云工控新建稀土永磁伺服电机系统项目","新增新建","建造建筑物1.6万平方米，其中生产车间1.4万平方米，办公及辅助用房2000平方米。项目建成后可年产稀土永磁电机30万台，实现年销售收入2.5亿元，利税1800万元左右。","2021-2022",15000,5000,"主体结构封顶。","制造业","是","双凤镇"]
[3,"艾斯派瑞新建新能源汽车电子及控制系统项目  ","新增新建","建筑面积约2.6万平方米，其中生产车间2.22万平方米，办公研发及辅房3800平方米，达产后可实现年销售新能源汽车电子及控制系统100万套，年产值3.5亿元，税收1500万元。","2021-2022",15000,8000,"主体结构封顶。","制造业","是","双凤镇"]
[4,"恩力稳新建航天及汽车用密封产品项目","新增新建","建造建筑物2万平方米，年产汽车用密封件1000万件。","2021-2022",16000,8000,"主体结构封顶。","制造业","是","双凤镇"]
[5,"车视杰新建车用电子产品项目","新增新建","建造建筑物1.2万平方米，其中生产车间1.05万平方米，办公及辅房1500平方米。达产后年产摄像头200万只，新增年产值2亿元，利税1000万元。","2021-2022",12000,6000,"主体结构封顶。","制造业","是","双凤镇"]
[6,"成煜新建智能家居新型材料项目","新增新建","建造建筑物2万平方米，目前公司正积极申报省高新技术企业，新项目计划设计建设高标准智能化生产及物流车间。项目达产后实现产值2.5亿元。","2021-2022",16000,8000,"主体结构封顶。","制造业","是","双凤镇"]
[7,"摩创迁扩建精密塑料零件等产品项目","新增新建","租赁厂房9500平方米。项目达产后年产精密塑料零件300吨、精密五金零件100吨、模具200套。",2021,10000,10000,"投产。","制造业","是","双凤镇"]
[8,"剑派新增新能源汽车紧固件制造项目","新增新建","建造建筑物4.3万平方米，其中生产车间3.98万平方米，办公及辅助用房3200平方米。项目建成后可年产新能源汽车紧固件1.2万吨，实现新增年销售收入1.5亿元，新增利税2000万元左右。","2021-2022",12000,10000,"主体框架完工。","制造业","是","双凤镇"]
[9,"太仓华丽企业管理有限公司新建酒店项目","新增新建","项目总建筑面积约为2万平方米，建设定位为旅游、度假、休闲、娱乐、康养、会务等性质的综合性旅游度假酒店。建成后年效益约为300万元。","2021-2022",17000,10000,"结构封顶。","服务业","是","双凤镇"]
["△10","申江通科技新建云数据数字通讯项目","结转续建","项目总建筑面积12万平方米。主要从事通信设备、电气机械和器材、光电子器件、传感器、发电机组的研发、生产、销售。项目建成后生产、装配和组装微模块和小母线等产品，并提供大数据应用，年产IT机柜12000台、微模块1000组、小母线1000组。项目年产值8亿元。","2020-2021",302000,150000,"竣工。","制造业","否","双凤镇"]
["△11","太仓再生资源综合利用项目","结转续建","处理生活垃圾2250吨/日，配置3×750吨/日的炉排焚烧炉，3台中温次高压余热锅炉，1台45MW抽凝式汽轮发电机组和1台25MW抽凝式汽轮发电机组。其中一期建设2×750吨/日的炉排焚烧炉，2台中温次高压余热锅炉，1台45MW抽凝式汽轮发电机组；二期建设1×750吨/日的炉排焚烧炉，1台中温次高压余热锅炉，1台25MW抽凝式汽轮发电机组。处理易腐垃圾400吨/日，其中一期建设规模200吨/日，二期建设规模200吨/日；建设1座有效库容约50万立方米的飞灰填埋场。","2020-2022",170000,50000,"完成工程量节点三分之一。","生态环保","否","双凤镇"]
["八、市属（5个）",{"$nulls":4},1626600,168000]
["☆1","苏锡常城际铁路太仓先导段（上海嘉闵线北延至太仓段）","新增新建","包含苏锡常都市快线与嘉闵线衔接工程先导段太仓站至白云渡路至十八港路至省界段，线路总长约10千米，另含车辆段1处、主变电所1座。车辆段近期规模为23条存车线、4线检查库。","2021-2026",1300000,30000,"完成前期工作，开工建设。","基础设施","是","交运局"]
[2,"太仓市产业资本中心项目","新增新建","项目占地面积28亩，建设包括银行、基金机构等多家金融机构并提供金融服务的综合载体。","2021-2023",80000,18000,"桩基和围护工程结束，开始地下开挖。","科创载体","是","资产集团"]
[3,"苏昆太高速太仓北互通（沪宜高速公路金仓湖互通）","新增新建","该互通位于苏昆太高速双凤出口与沿江枢纽之间，用四条半直连匝道上跨沪宜高速，且四条匝道均为桥梁形式，全长1279米，并建设收费站及站房。","2021-2023",21600,10000,"完成桥梁下部结构。","基础设施","是","交运局"]
[4,"256省道太仓沙溪至双凤段工程","新增新建","新建道路全长4.63公里，一级公路标准，沥青砼路面，双向四车道，红线宽40米（盐铁塘大桥一座）。","2021-2023",45000,30000,"完成拆迁开工建设，完成路基及桥梁下部结构。","基础设施","是","交运局"]
["△5","太仓港港口支线铁路","结转续建","沪通铁路太仓港站至浮桥集装箱装卸作业区，正线长约13.2公里，包括太仓港站上行疏解线2.24公里，浮桥装卸场牵出线1.5公里、联络线0.45公里。","2019-2021",180000,80000,"建成投运",null,"否","港口委"]
["注：“☆”为省重大项目；“△”为苏州市重点项目。"]